## Tabelle1
Sprint Review Protocol
Sprint No: |  | 5
Date & Time |  | 2026-05-12
Group Number |  | 4
Participant 1 |  | Sotiriou Antonios
Participant 2 |  | Karabacek-Shahri Niloufar
Participant 3 |  | Karadeniz Alev
Participant 4 |  | Döberl Julian
Participant 5 |  | Schubart Ermylos
Mentor |  | Elmin Smajlovic
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | Spider and Snake Enemies | 8 | 10 | 2 | 1 |  | Two new Enemies with their ASCII
2 | Implementing more Rooms | 10 | 6 | -4 | 1 |  | 3x3 Grid for start then Textures
3 | Texture Class and Textures | 10 | 5 | -5 | 1 |  | Textures to avoid many Classes
4 | Item und Relic Classes | 6 | 11 | 5 | 1 |  | Pick up Item and stats Increase
5 | ChaseMovement | 6 | 3 | -3 | 1 |  | Chase the player when in radius
6 | Team meetings | 2 | 2 | 0 | 1 |  | Standart Meeting every 2 Weeks
7 | Documentation | 1 | 1 | 0 | 1 |  | Document all Classes
8 | Quit Dialog | 2 | 2 | 0 | 1 |  | Ask player if really wants to Quit
9 | Terrain ASCII | 4 | 5 | 1 | 1 |  | Changed Terrain ASCII to birdseye
10 | GuardingMovement | 5 | 2 | -3 | 1 |  | The Entity moves on a path.
|  |  |  | -7 | 10 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol