## Tabelle1
Sprint Review Protocol
Sprint No: |  | 6
Date & Time |  | 2026-06-09
Group Number |  | 4
Participant 1 |  | Sotiriou Antonios
Participant 2 |  | Karabacek-Shahri Niloufar
Participant 3 |  | Karadeniz Alev
Participant 4 |  | Döberl Julian
Participant 5 |  | Schubart Ermylos
Mentor |  | Elmin Smajlovic
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | Player Stats at bottom of screen | 3 | 2 | -1 | 1 |  | Show all important player stats.
2 | Different Texture for each Room | 5 | 2 | -3 | 1 |  | Should be obvious upon enter
3 | Gatekeeper Class Game goal | 5 | 13 | 8 | 1 |  | Gatekeeper demand relics number
4 | More relics for each room | 5 | 7 | 2 | 1 |  | Random positioning in each Room
5 | Animations für Relics and Player | 5 | 5 | 0 | 1 |  | Fix Frames Per Second Animations
6 | Battle against more Enemies | 2 | 2 | 0 | 2 |  | Player against more enemies at once
7 | Documentation | 3 | 4 | 1 | 1 |  | Protocols, Sprints and Github Issues
8 | Meeting | 2 | 2 | 0 | 1 |  | Meeting between Project Members
9 | Enemy aggression Animation | 3 | 6 | 3 | 1 |  | Trigger when player in range
n |  |  |  | 0
9 |  |  |  | 10 | 9 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol