## Tabelle1
Sprint Review Protocol
Sprint No: |  | 2
Date & Time |  | 2026-03-24
Group Number |  | 4
Participant 1 |  | Sotiriou Antonios
Participant 2 |  | Karabacek-Shahri Niloufar
Participant 3 |  | Karadeniz Alev
Participant 4 |  | Döberl Julian
Participant 5 |  | Schubart Ermylos
Mentor |  | Elmin Smajlovic
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | Game Architecture, Story, Plot … | 11 | 13 | 2 | Passed |  | Game Design Document, Logo.
2 | Entity Class erweitern. | 6 | 6 | 0 | Passed |  | Funktionalität, animieren Basis.
3 | Vec2d Class erweitern. | 8 | 7 | -1 | Passed |  | Vektor Mathe, Path finding.
4 | Player, Enemy, EntityManager | 8 | 8 | 0 | Passed |  | Game Mechaniks. Dynamic render.
5 | BattleManager erweitern | 8 | 13 | 5 | Passed |  | Battle Mechanics, buffs debuffs.
6 |  |  |  | 0
7 |  |  |  | 0
… |  |  |  | 0
… |  |  |  | 0
n |  |  |  | 0
7 |  |  |  | 6 | 0 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol