## Tabelle1
Sprint Review Protocol
Sprint No: |  | 7
Date & Time |  | 2026-06-23
Group Number |  | 4
Participant 1 |  | Sotiriou Antonios
Participant 2 |  | Karabacek-Shahri Niloufar
Participant 3 |  | Karadeniz Alev
Participant 4 |  | Döberl Julian
Participant 5 |  | Schubart Ermylos
Mentor |  | Elmin Smajlovic
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | Presentation Video | 3 | 5 | 2 | 1 |  | Gameplay und Keybindings zeigen
2 | Short User Manual | 2 | 3 | 1 | 1 |  | Ein kurze User manual des Spiels
3 | Game Design Document update | 2 | 12 | 10 | 1 |  | Aktuallisieren auf neuesten Zustand
4 | Deploy Manual | 2 | 4 | 2 | 1 |  | Erklären, das Spiel installiert wird
5 | Presentation Power Point | 3 | 6 | 3 | 1 |  | Presentation des gesamten Projekts
6 | Transition on enemy collision | 2 | 2 | 0 | 1 |  | Glatt wechseln zur Kampffenster
7 | Random Number of Relics | 2 | 2 | 0 | 1 |  | Gatekeeper verlangt zufällig
8 | Transition Screen on game restart | 2 | 4 | 2 | 1 |  | Wird ein ASCII-Stoppuhr angezeigt
9 | Screen resolution adopt | 2 | 3 | 1 | 1 |  | Anpassen zur Bildschirmdiagonale
n |  |  |  | 0
9 |  |  |  | 21 | 9 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol