## Tabelle1
Sprint Review Protocol
Sprint No: |  | 3
Date & Time |  | 2026-04-07
Group Number |  | 4
Participant 1 |  | Sotiriou Antonios
Participant 2 |  | Karabacek-Shahri Niloufar
Participant 3 |  | Karadeniz Alev
Participant 4 |  | Döberl Julian
Participant 5 |  | Schubart Ermylos
Mentor |  | Elmin Smajlovic
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | Gamephysics, Attack Direction | 10 | 4 | -6 | Passed |  | Direction normal vector
2 | Enemy movement, Documentation | 6 | 7 | 1 | Passed |  | Random movement for Enemies
3 | Battle working example | 10 | 4 | -6 | Passed |  | Start, fight or cancel
4 | Entity Bounds update with move | 8 | 7 | -1 | Passed |  | Update Bounding Box when moving
5 | In bounds movement | 8 | 7 | -1 | Passed |  | Player unable to move out of Screen
6 |  |  |  | 0
7 |  |  |  | 0
… |  |  |  | 0
… |  |  |  | 0
n |  |  |  | 0
7 |  |  |  | -13 | 0 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol