## Tabelle1
Sprint Review Protocol
Sprint No: |  | 1
Date & Time |  | 2026-03-04
Group Number |  | 4
Participant 1 |  | Sotiriou Antonios
Participant 2 |  | Karabacek-Shahri Niloufar
Participant 3 |  | Karadeniz Alev
Participant 4 |  | Döberl Julian
Participant 5 |  | Schubart Ermylos
Mentor |  | Elmin Smajlovic
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | Game Loop, Documentation | 11 | 17 | 6 | Passed |  | Fix Framerate, Coordination
2 | class Entity | 11 | 11 | 0 | Passed |  | Rule of five, Algemeine Attribute
3 | class Vec2d | 11 | 11 | 0 | Passed |  | Rule of five, vektor math functions
4 | Kollisionserkenung | 11 | 13 | 2 | Passed |  | Bounding-box, Cirlce-Cirlce
5 | class BattleManager | 11 | 13 | 2 | Passed |  | Rule of five, Battle Coordination
6 |  |  |  | 0
7 |  |  |  | 0
… |  |  |  | 0
… |  |  |  | 0
n |  |  |  | 0
7 |  |  |  | 10 | 0 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol