## Tabelle1
Sprint Review Protocol
Sprint No: |  | 4
Date & Time |  | 2026-04-28
Group Number |  | 4
Participant 1 |  | Sotiriou Antonios
Participant 2 |  | Karabacek-Shahri Niloufar
Participant 3 |  | Karadeniz Alev
Participant 4 |  | Döberl Julian
Participant 5 |  | Schubart Ermylos
Mentor |  | Elmin Smajlovic
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | Room Class with ASCI art | 7 | 8 | 1 | Passed |  | Basic Class to represent a Room
2 | Item Basis Class for all items | 6 | 8 | 2 |  | failed | Player should pick up an Item
3 | Gatekeeper Class, (friendly NPCs) | 6 | 8 | 2 | Passed |  | Player wins upon collision
4 | Follow Player Movement. | 10 | 6 | -4 |  | failed | When player in radius, haunt him
5 | BattleManager Ascii, Winner | 4 | 5 | 1 | Passed |  | Game over when Player looses
6 | Meetings | 2 | 2 | 0 | Passed |  | Meetings between Team members
7 | Documentation | 1 | 1 | 0 | Passed |  | Basic Class functionality description.
… |  |  |  | 0
… |  |  |  | 0
n |  |  |  | 0
7 |  |  |  | 2 | 0 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol